## Slide 1: Commissioning of the LHC superconducting magnets systems: Why an LHC Hardware Commissioning? Specificity and complexity of this machine
Roberto Saban – 2008 Academic Training Lecture 1

## Slide 2: The prototype test String 2

## Slide 3: experience

## Slide 4: the mandate
individual system tests
hardware commissioning

After the qualification for operation of the individual systems of a sector (vacuum, cryogenics, quench protection, interlocks, powering, etc.),


each sector will be commissioned as a whole up to the powering to nominal current of all the circuits.
Validation and specific studies will be carried-out on the first commissioned sector.
What tests
  the procedures and the sequence
How
  what conditions are required to start
  what conditions determine it is finished
  what conditions are required during the tests
Sytem owners define and carry-out
Hardware Commissioning Coordination ensures that the conditions required exist
What tests
  the procedures and the sequence
How
  what conditions are required to start
  what conditions determine it is finished
  what conditions are required during the tests
Hardware Commissioning Coordination with System Owners define and carry-out
and ensures that the conditions required exist

## Slide 5: commissioning the superconducting circuits

## Slide 6: the sectors of LHC
The LHC is composed of
eight cryogenically independent sectors
fed from four feed points

## Slide 7: the sectors of LHC
The LHC is composed of
eight electrically independent sectors
each fed from a UA, an RR, a UJ and sometimes a USC
UA47
RR53
USC55

## Slide 8: the circuits of a sector of LHC
4.5 K
4.5 K
1.9 K
1.9 K
157 circuits
6 circuits
14 circuits
13 circuits
Totalling 190 circuits

## Slide 9: the electrical subsectors of an LHC sector

## Slide 10: the superconducting magnets
The arc: Most of a sector is composed of 154 dipoles and 40 quadrupoles which
  are in series: dipoles in series & quads in series
  operate at 1.9 K
  the dipoles have a huge inductance 16H
  contain
    families of correctors in series
    dipole correctors
The matching sections: small subsectors
  operating at 4.5K
  often standalone magnets
  very special – often unique - magnets
The inner triplet: composed of very high gradient quadrupoles and a dipole which
  operate at 1.9K
  contains a complex electrical circuit with nested converters
The coupling via the QRL
All coupled via the headers in the cryogenic distribution line
Any repair or exchange of a component has an impact on the whole sector

## Slide 11: the dipole circuit
3 km
154 dipoles
Circuit inductance 16 H
Energy stored at nominal current (11.850 A) is 1.12 GJ per sector
The large magnetic energy (1.12 GJ) stored in the magnets of one sector (2.5 x Hera) requires extremely reliable systems to detect failures and safely dump the energy in a controlled way

## Slide 12: the quench detection system
Quench detectors
Current leads
Local on each dipole
Global detectors on the bus bars
The current leads
Typical resistance 7 μΩ
Threshold is 3 mV during 1 s
Magnets
U_res = U_1+ U_2
Threshold is 100 mV during 10 ms
Bus
U_res = U_bb_1+ U_bb_2 – N ( U_mag_A+ U_mag_B)/2
Threshold is 1V during 1 s
U = R x I

## Slide 13: what needs to be tested for the cryogenic system
Cryogenic plants of unprecedented capacity (18 kW at 4.5 K) and including main components at the frontier of today’s technology (cold compressors for the 1.8 K refrigeration unit)
Technological frontier
Full scale validation of cooling scheme (cool down and warm ups, quench recovery, redundancy)
Cryogenic circuit integrity
DFB & CL
Instrumentation
Leak tightness
Insulation vacuum
Commissioning of the complete cryogenic system

## Slide 14: the cooling scheme
vacuum vessel

## Slide 15: Helium II in the LHC
λ line
Saturated He II
Pressurized He II

## Slide 16: what needs to be tested for the power converters
Regulation loop
Free-wheel system at nominal current with high time constant
Compatibility with QPS at start up
Tracking
Inner triplet
Technological frontier
2ppm
Power converters with unprecedented precision (a few ppm) over a very large dynamic range (104)

## Slide 17: the superconducting circuits: the inventory
Industrial quantities
Circuit Type | Sector |  |  |  |  |  |  |  | LHC
 | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7 | 7-8 | 8-1 | 
13 kA | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 24
Independently Powered Dipoles | 3 | 2 | 2 | 3 | 1 | 0 | 2 | 3 | 16
Independently Powered Quadrupoles | 14 | 7 | 6 | 13 | 12 | 5 | 7 | 14 | 78
600A with Energy Extraction | 23 | 27 | 28 | 24 | 23 | 27 | 27 | 23 | 202
600A Energy Extraction in Converter | 14 | 20 | 20 | 14 | 14 | 20 | 20 | 14 | 136
600A no Energy Extraction | 16 | 9 | 2 | 9 | 9 | 2 | 9 | 16 | 72
80-120A Correctors | 50 | 37 | 22 | 33 | 33 | 22 | 37 | 50 | 284
TOTAL | 123 | 105 | 83 | 99 | 95 | 79 | 105 | 123 | 812
Circuit Type | Sector |  |  |  |  |  |  |  | LHC
 | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7 | 7-8 | 8-1 | 
60A Closed Orbit Correctors | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 752

## Slide 18: the methodology
Industrial quantities
Interlock tests of a powering subsector prior and after connection of the power cables to the DFB leads
Power Converters
connected to Magnets
Power Converters
not connected to Magnets
300 K
1.9 K
90 K
Test of power converters connected to the DC cables in short circuit, including controls for powering, ramp, monitoring
connexion of power cables
to the current leads
Electrical Quality Assurance
Individual System Tests of the Quench Protection and Energy Extraction Systems
Post-Mortem System tests
Commissioning of the electrical circuits one by one or in groups at low, intermediate and nominal currents
Commissioning of all the electrical circuits of the sector powered in unison to nominal current with nominal ramp rates
Individual System Tests of Powering Interlock Control

## Slide 19: the methodology for the test procedures & automation of procedures and analysis
Industrial quantities
The objectives are:
the validation of the protection strategies under the different failure scenarios and
the evaluation of the behavior and of the performance of
  the magnet chain,
  the current leads and
  the power converters
during a normal LHC ramp, in steady state and during a ramp down of the current.

## Slide 20: the methodology for the test procedures & automation of procedures and analysis
Industrial quantities
Verification of the Protection Interlocks
Configuration of the Power Converter
Verification of the Energy Extraction System at different current levels

## Slide 21: the methodology for the test procedures & automation of procedures and analysis
Industrial quantities

## Slide 22: automation of procedures
Industrial quantities
Approved and reproducible test sequences
Assistance to operators
Automatic recording of test results

## Slide 23: computer assisted analysis
Industrial quantities

## Slide 24: quality control
Industrial quantities
Automated recording but also manual data entry
Provides data for analyis tools
Ensures perennity of data

## Slide 25: real-time follow up of tests

## Slide 26: standard technologies
Normal AC distribution
UPS AC distribution
Ventilation
Demineralized water
Networks
Fieldbuses
Controls equipment
Standard technologies

## Slide 27: the short circuit tests
UJ33
RR57-UJ56
RR73 UJ76
RR77
UA83
RR53-USC55
UA87
UA23
UA27
UA43
UA47
UA67
UA63
RR13-UJ14
RR17-UJ16
15 underground areas

## Slide 28: the short circuit tests
Power converter
Powering interlock controller
Energy extraction system
DC cables
Ventilation
Cooling water
AC distribution
Networks
Fielbuses
Gateways

## Slide 29: the short circuit tests
kW
Pt6
S67
 | Zone1+UJ66 | Zone2 | Zone3 | Zone4 | Zone5 | Zone6 | Zone7 | Zone8 | Zone9 | Zone10
Vent. | 15kW | 15+15 kW | 15+15 kW | 15 kW | 15 kW | 15kW | 15kW | 50kW | 15kW | 15kW
Syst. | 0kW | 16 kW | 4 kW | 32 kW | 10 kW | 2 kW | 10 kW | 50 kW | 38 kW | 40 kW
m | 24 | 19.8 | 20.2 | 18.9 | 21 | 22.2 | 27 | 13.8 | 16.5 | 24
Beam dumping system
and Power
Converters
Electrical
Substation
Main
dipole
PC
600A PC
EE racks
Main
quads
PCs
EE
Vacuum Cryogenics
Beam diagnostics
MS
Power
Converters
Beam dumping system
Power
Cables
Power
Cables
MS
Power
Converters
UA67
Tot
215kW
215kW
Addition of ventilation ducts and of local ventilation units
Measurement of ambient air temperature close to the electronics racks

## Slide 30: the short circuit tests
Measurement of cable temperature during the 24-hour run

## Slide 31: support to operation: infrastructure systems
Before global commissioning of complex/large systems can start
  the individual commissioning of the infrastructure systems is carried out
  tuning with the load is carried out
  heat runs are carried out
  performance is measured and recorded
  frequent and multiple adjustments are carried out
  performance is monitored throughout the commissioning
  surprises are often encountered
Standard technologies

## Slide 32: Access safety and control systems
Standard technologies
The LHC access system was commissioned during the first week of January 2008 by a joint team in collaboration with the supplier's team.
From early April access to the LHC is possible with dosimeter and biometric control.
All the sectors in Hardware Commissioning today make use of the system
We want to
  ensure that people who do not need to be there cannot access the sector
  be sure that nobody is in there during the first cool down and the first warm up as well as when we power a sector
  learn how to use the system
  commission the system

## Slide 33: coupling and interdependencies of the systems
  complexity for the diagnostics
    quantity of signals spread over different systems
    variety of instrumentation (voltage taps, current sensors, heaters, cryogenic instrumentation, etc.)
  interdependency for safe operation
    interlocks,
    QPS,
    PCs
    but also cooling, ventilation, AC distribution – normal, UPS, safety network
Coupling of the systems

## Slide 34: interdependencies of the systems
Coupling of the systems

## Slide 35: Geographical distribution
Geographical distribution
50 m x 50 m
up to 100 m
30 m x 30 m
3’000 m

## Slide 36: Software for operation, controls and diagnostics
Dry runs
  Injection kickers system
  LHC Beam dumping system (kickers, energy tracking, diagnostics,)
  Beam instrumentation (loss monitors, position monitors, current transformers, screens)
  Power converters in simulation mode
  Collimators
  Timing system
  Communication with experiments (handshakes, modes, fill number, beam based measurements, etc.)
  Post mortem data acquisition system
  Squeeze
Using the final software foreseen for operation for the commissioning of the machine systems
  Sequencer
  Logging system
  Post mortem system
  On-line databases
  Industrial supervision systems
1
2

## Slide 37: ... in summary
Technologies at or beyond the start of the art
  Superconducting magnets operating close to the limit of the load line
  Cryogenic plants of unprecedented capacity (18kW at 4.5K) and including main components at the frontier of today’s technology (cold compressors at 1.8K)
  Power converters with unprecedented precision (a few ppm) over a very large dynamic range (104)
  Each sector stores a large magnetic energy (1.2 GJoule) in the magnets (2.5 x Hera) and therefore requires extremely reliable systems to detect quenches and safely dump the energy in a controlled way
High tech components in industrial quantities (1800 circuits, large circuits 154 dipoles, 16 H, 12kA) which justifies
  methodology for test procedures,
  automation of procedures and analysis
  quality control

## Slide 38: ... in summary
Standard technologies
  in infrastructure systems (electrical, ventilation, water cooling, networks, fieldbuses, control infrastructures, etc.)
  in large quantities,
  various types and
  stretching over large distances
Coupling and interdependencies of the systems
  complexity for the diagnostics (quantity of signals, spread over different systems ) & instrumentation (voltage taps, current sensors, heaters, flow meters, cryogenic instrumentation, etc.)
  interdependency for safe operation (interlocks, QPS, PCs but also cooling, ventilation, AC distribution – normal, UPS, safety network)
Geographical distribution which
  extends the size of the installation (e.g. cryogenics: surface buildings 50 x 50 m, shafts 100 m deep, tunnel 2 x 3 km long)

## Slide 39: the superconducting circuits but also all the other systems
the beam dumping system
the injection systems
the warm magnets
the RF system
the collimators
the beam instrumentation

## Slide 40: ... where are we today cool down status

## Slide 41: ... where are we today cool down status
Sector | Average T [K] | Status
12 | 300 | Flushing
23 | 22 | Cool down
34 | 177 | Cool down
45 | 300 | Commissioned to 5 TeV except for the triplet Inner triplet now connected Consolidation complete Cool down starts in two weeks
56 | 2 | Fully commissioned to 5 TeV Dipoles and quadrupoles being trained to 7 TeV
67 | 25 | Cool down
78 | 2 | Partially tested in June 2007 Inner triplet connected Powering tests start tomorrow
81 | 2 | Powering tests start in one week

## Slide 42: ... where are we today powering tests of sector 56
Open
Days
400 kV power cut
Easter
Week end
ML6
ARC
LR5
XR5
Week end
Week end
400 kV power cut
May 1st + Ascension
Week end
Training campaign on the dipoles starts
Powering Groups of Circuits

## Slide 43: ... where are we today powering tests of sector 56
A strategy, where the initial beam energy is at least 5 TeV, is proposed to gain time with the training of magnets and meet the summer deadline.
The fact that we can easily reach that energy level has been proven both in Sector 45 and Sector 56.
Nevertheless, we have started a quench campaign on the dipoles of Sector 56 to find out how much time we will need to get to 7 TeV.
Current [A] | Equivalent Energy [TeV] | Magnet (Position) | Date
10004 | 5.91 | 3362 (A28L6) - 2245 (B29R5) | 28/04/08
10227 | 6.04 | 3370 (A29L6) | 28/04/08
10357 | 6.12 | 3372 (A23L6) | 29/04/08
10546 | 6.23 | 3188 (A15R5) | 30/04/08
10652 | 6.29 | 3368 (C32R5) | 06/05/08
10714 | 6.33 | 3246 (A10L6) - 3387 (C16L6) | 07/05/08
10751 | 6.35 | 3335 (A21R5) | 09/05/08